## Project Version Control
PROJECT
Project Title: |  | Project Manager:
Project Reference: |  | Principal Designer:
Date: |  | Principal Contractor:
DOCUMENT CONTROL
Distribution: hard/soft copy
Prepared By | Name | Position | Date
HSI12
Distributed to | Name | Position | Date
VERSION CONTROL
Version Control: hard/soft copy
Version | Date Issued | Summary of change | Produced /Revised by
The latest version of this document can be located at | <insert location here>

## Risk Register
Design Stage Risk Register (HSI-12)
Project: XXX | [8 empty] | Location: |  |  |  |  | Stage:
Identifier | Discipline team | LOCATION | HAZARD/CONSTRAINT | CONSEQUENCE OF HAZARD | Type (health, safety, environemntal, lack of information) | RISK LEVEL BEFORE MITIGATION |  |  | Risk Owner | Next Formal Risk Review | MITIGATION MEASURES TAKEN BY THE DESIGNER AND THE LOCATION OF SUPPORTING INFORMATION | RISK LEVEL AFTER MITIGATION |  |  | Residual Risk on Drawing (Y/N) & SHE Box text | GUIDANCE MEASURES THAT COULD BE APPLIED BY THE CONTRACTOR (OR OTHERS)
|  | OF HAZARD |  | (RISK) |  | Likelihood | Severity | Risk |  |  |  | Likelihood | Severity | Risk
XXX001 | BR - Bridges |  | Vehicles getting to site - Movement on the public highway increasing traffic during shingle and material transportation. | Potentially leading to increased number of road accidents involving damage to infrastructure or potential injury/death. |  | 5 | 5 | 25 | AR - Designer 1 | Detailed Design | Review haulage routes and any interaction with pedestrians. Review ingress and egress points to working areas from highways and plan safe access. Undertake a review of material delivery methods and size of plant required to ensure safe delivery. | 1 | 5 | 5 |  | Contractor to produce a traffic management plan to reduce risk of traffic related incidents. Contractor to agree access and egress routes prior to start of work. Review the use of convoys. Contractor is to carefully manage police movements on site.
XXX002 | [5 empty] | 2 | 3 | 6 | [5 empty] | 0
XXX003 | TN - Tunnels | [6 empty] | 0 | [5 empty] | 0
XXX004 | [7 empty] | 0 | [5 empty] | 0
XXX005 | EV - Environmental | [6 empty] | 0 | [5 empty] | 0
XXX006 | HW - Highways | [6 empty] | 0 | [5 empty] | 0
XXX007 | [7 empty] | 0 | [5 empty] | 0
XXX008 | [7 empty] | 0 | [5 empty] | 0
XXX009 | [7 empty] | 0 | [5 empty] | 0
XXX010 | [7 empty] | 0 | [5 empty] | 0
XXX011 | [7 empty] | 0 | [5 empty] | 0
XXX012 | [7 empty] | 0 | [5 empty] | 0
XXX013 | [7 empty] | 0 | [5 empty] | 0
XXX014 | [7 empty] | 0 | [5 empty] | 0
XXX015 | [7 empty] | 0 | [5 empty] | 0
XXX016 | [7 empty] | 0 | [5 empty] | 0
XXX017 | [7 empty] | 0 | [5 empty] | 0
XXX018 | [7 empty] | 0 | [5 empty] | 0
XXX019 | [7 empty] | 0 | [5 empty] | 0
XXX020 | [7 empty] | 0 | [5 empty] | 0
XXX021 | [7 empty] | 0 | [5 empty] | 0
XXX022 | [7 empty] | 0 | [5 empty] | 0
Likelihood: |  |  |  | Severity: | [5 empty] | Risk: | Likelihood x Severity
1 - Improbable - Extremely unlikely to occur in relevant period |  |  |  | 5 - Catastrophic - Death or major loss; total systems failure
2 - Remote - Unlikely to occur in relevant period |  |  |  | 4 - Critical - Major injury, major damage to property/ infrastructure, or major environmental effect. | [5 empty] | 16-25 | Very High Risk - Unacceptable. Re-examine activities to provide lower risk.
3 - Occasional - Likely to occur in relevant period |  |  |  | 3 - Serious - Lost time injury or illness; minor damage to property/infrastructure or significant environmental effect. | [5 empty] | 9-15 | High Risk - Apply further mitigation measures and/or alter method of work to reduce risk further. Seek Project Manager approval if risk cannot be reduced.
4 - Probable - Likely to occur several times in relevant period |  |  |  | 2 - Marginal - Minor first aid incident or requiring routine maintenance repair. | [5 empty] | 6-8 | Medium Risk - Tolerable only if further mitigation is not reasonably practical and there is a need to continue activity with identified controls.
5 - Frequent - Likely regular occurrence in relevant period |  |  |  | 1 - Insignificant - Unlikely to have impact on works. | [5 empty] | 1-5 | Low Risk - Broadly acceptable if all reasonably practicable control measures in place.
Prepared by: | [5 empty] | Title: | [6 empty] | Date:
Reviewed by: | [5 empty] | Title: | [6 empty] | Date:
Approved by: | [5 empty] | Title: | [6 empty] | Date:

## Instructions
INSTRUCTIONS
1.0 Introduction
1.1 The Design Stage Risk Register (HSI-12) assists in discharging responsibilities under the CDM 2015 Regulations. After identification of the hazards on site, this template is to be used to record and manage risks associated with the project. Its purpose being to eliminate, reduce or control foreseeable risks that may arise during construction. This will assist the principal contractor in helping them plan, manage, monitor and coordinate health and safety during the construction phase.
1.2 The objective of CDM is to secure Health and Safety management in all construction projects. Through key elements including: a. managing risks using principles of prevention. b. appointment of the right people and organisations at the right time c. providing information, instruction, training and supervision d. duty holders cooperating and communicating, coordinating with each other e. consulting with the workforce.
1.3 Your responsibility
a. This is a LIVE document and must be subject to regular review throughout the lifecycle of the project, records of which should be retained and readily retrievable. Note: the information provided will be relevant to the scale and complexity of the project:
1.4 Requirements
a. CDM 2015 requires designers to: ‘eliminate, so far as is ‘Reasonably Practicable’, (SFARP) Foreseeable Risks to the health or safety of any person
b. ‘Foreseeable Risk’ - A likelihood of injury or damage that a reasonable person (competent engineer at equivalent position) should be able to anticipate in a given set of circumstances
c. ‘Reasonably Practicable’ has been defined - “balancing the level of risk against the measures needed to control the real risk in terms of money, time and trouble
d. Do not need to take action if it would be grossly disproportionate to the level of risk.
e. 'grossly disproportionate' test in UK construction law (CDM 2015) determines if a safety measure is 'Reasonably Practicable' by comparing risk against cost/time/trouble.
Hazard and Risk Evaluation Matrix
|  | Impact, severity, consequence | Insignificant | Marginal | Moderate | Critical (A fatality or 1 or more people harmed) | Catastrophic (Multiple deaths)
Designers: Designers are responsible for undertaking Design Risk Management (Hazard mitigation) following the acronym ERIC (Eliminate, Reduce, Isolate or Inform, or control) in the order written when considering construction sequence, materials selection, notes on drawings and specifications. This subsequently extends into use, operation, maintenance and demolition of the asset. a. Designers must focus on H&S information to ensure that people would not reasonably anticipate b. be specific to the project c. reflect the complexity of the project d. communicate the risks effectively on reports and drawings as applicable Principal Designer: Ensure all CDM duty holders complete and contribute to the Risk register. Commutation and transfer of residual risks to Principal Contractor, Specialist Contractors, Client, Operators and Maintainers. Operators/ Maintainers: Use of residual Principal Contractor: The Principal Contractor is responsible for using the (PCI) information received, management of H&S and residual risks including information provided by Principal Designers, construction methodology and informing all other contractors and updating any residual risks. Operators/ Maintainers: Use of residual risks within the H&S File by those who need it | Risk matrix for an event, incident or circumstance |  | ~ Minor injuries / slight harm non first aid, ~ Impairment of performance or function lasting less than 1hrs, able to return to work/normality within 8hrs ~ minor damage or loss (<£50k) | ~Injuries requiring Medical First Aid but no lost time, ~ Impairment of performance or function lasting up to 24hrs ~ moderate damage or loss (£50-150K) | ~ Moderate harm: ~ Moderate injury and illness with lost time. ~ Impairment of performance or function lasting 7 days +, Able to return to work /normality after extended period. ~ substantial damage or loss - (£150k to £1.0m). | ~ Major / severe harm, ~ Single fatality, including suicide or long-term disability, permanent life changing injury or impairment, may require long-term treatment for remainder of life, ~ Never able to return to work. ~ significant external medical intervention sought. ~ Major damage or loss (£1- 1.5m) | ~ Extreme Harm: ~ Multiple fatalities ~ Extreme loss or damage (£1.5m +)
| Likelihood | Eliminated (0) | 1 | 2 | 3 | 4 | 5
2.0 Design Risk Register The designer must focus on significant, foreseeable, unusual, complex or difficult-to-manage - not obvious to a competent contractor or designer risks. | ~ Very low: ~ extremely / very unlikely ~ highly improbable | 1 | Low (1) | Low (2) | Low (3) | Low (4) | High (5)
2.1 Column A - Create a unique identifier linked to the Project name XXX001. This will be used as the identifier within drawings and reports | ~ Low ~ unlikely ~ seldom, | 2 | Low (2) | Low (4) | Medium (6) | Medium (8) | High (10)
2.2 Column B - Confirm the Discipline team. A dropdown has been created | Occasional, Medium may occur, may happen | 3 | Low (3) | Medium (6) | High (9) | High (12) | High (15)
2.3 Column C - Location should be consistent and agreed to avoid confusion. Please review the BIM and Asset management plan as applicable. UAID Unique asse identifier | ~ High ~ likely ~ probable | 4 | Low (4) | Medium (8) | High (12) | High (16) | Very High (20)
2.3 Column D - Hazard is defined as something with the potential to cause harm. (Example underground services) A constraint is identified as something that will constrain the project, including legal and environmental constraints. The designer must identify hazards that have a significant or unusual impact on the project. | Definite, ~ Very High ~ Highly / very likely ~ very probable or repeated | 5 | Medium (5) | High (10) | High (15) | Very High (20) | Very High (25)
2.4 Column E - The Designer must identify RISKS, the consequences of realising the impact of the hazard. The term ‘risk’ is used to encompass both hazard (the potential for harm) and risk (a measure of the likelihood and the severity of harm occurring) (Example Hitting underground service and explosion)
2.5 Column F - Type (health, safety, environmental, lack of information) - dropdown developed to demonstrate health, safety environmental and lack of CDM Preconstruction information. | Risk Low( 1-5) band |  | Residual risk arising is considered to be from a routine activity and industry practice is widely available to control the risk to SFAIRP (So far as is reasonably practicable).
2.6 Column G,H,I - Risk Evaluation Matrix before mitigation - see table Please note that the severity remains the same before and after mitigation. (Unless there is a material change) | Risk Medium (5-likelihood, 6-8) band |  | Residual risk arising is considered to be from multiple activities or single complex activity, requiring additional measures over those required for routine activities to control the risk to SFAIRP.
2.7 Column J - Designer name required | Risk High (5-Impact, 9-15) band |  | Residual risk arising is considered to be from a non-routine activity or of a highly specialised nature that requires complex control measures and specialist resources to control the risk to SFAIRP.
2.8 Column K - Next Formal Risk Review | Risk Very High (16-25) band |  | Requires project manager / director approval and recorded formal review.
2.9 Column L - Mitigation Measures taken by the Designer and location of the information. Please add name and date, including decisions made during the design process and assumptions made. The designer can consider a 'reasonably practicable' proportionate impact of risks. Document H&S considerations - keep a track of risks and the range of design options.
2.10 Column M,N,O - Risk Evaluation Matrix post mitigation - see table Please note that the severity remains the same before and after mitigation. (Unless there is a material change)
2.11 Column P Residual Risk on Drawing (Y/N) & SHE Box text The risk is identified by the unique identifier XXX001 - Underground utility SHE Box. There is an 11KVA underground service
2.12 Column Q Guidance measures that could be applied by the contractor and others are for information only. You can support buildability and next stage of design. You can cross-reference industry best practice and HSE guidance that can be considered by contractors or others. HSG57 Avoiding dangers from underground service.

## Working
Designer Name
AR - Architectural | Health | AR - Designer 1 | AR - Architectural
BR - Bridges | Safety | BR - Designer 2 | BR - Bridges
CL - Construction and Logistics | Environment | CL - Designer 3 | CL - Construction and Logistics
CV - Civil | PCI Gap | CV - Designer 4 | CV - Civil
DR - Drainage | H&S | DR - Designer 5 | DR - Drainage
EV - Environmental | HSE | EV - Designer 6 | EV - Environmental
FI - Fire | H&S & PCI Gap | FI - Designer 7 | FI - Fire
GT - Geotechnical | HSE & PCI Gap | GT - Designer 8 | GT - Geotechnical
HF - Human Factors and Ergonomics |  | HF - Designer 9 | HF - Human Factors and Ergonomics
HS - Health and Safety |  | HS - Designer 10 | HS - Health and Safety
HW - Highways |  | HW - Designer 11 | HW - Highways
IT - Information and Communications Technology |  | IT - Designer 12 | IT - Information and Communications Technology
LI - Lighting |  | LI - Designer 13 | LI - Lighting
LP - Land and Property |  | LP - Designer 14 | LP - Land and Property
LS - Landscaping |  | LS - Designer 15 | LS - Landscaping
MEP - Mechanical, Electrical & Public Health |  | MEP - Designer 16 | MEP - Mechanical, Electrical & Public Health
OM - Operations and Maintenance |  | OM - Designer 17 | OM - Operations and Maintenance
RA - Railway |  | RA - Designer 18 | RA - Railway
SC - Security |  | SC - Designer 19 | SC - Security
SI - System Intergration |  | SI - Designer 20 | SI - System Intergration
ST - Structural |  | ST - Designer 21 | ST - Structural
SU - Sustainability |  | SU - Designer 22 | SU - Sustainability
TN - Tunnels |  | TU - Designer 23 | TN - Tunnels
TP - Town and Country Planning |  | TP - Designer 24 | TP - Town and Country Planning
UT - Utilities |  | UT - Designer 25 | UT - Utilities
PC - Principal Contractor

## HSI 12 Template Doc Control
HSI 12 - Design Stage Risk Register Template
Template Version | 3
Template issue date | 2026-07-01